## Cost
Deliverables for BEC test | [6 empty] | update: | 2 Sept 2003
NN | Part | Q.ty | Responsible | Status | Unit Cost | Total Cost | CORE/RND | Sharing
1. | Subracks
1.1 | VME 9U Air cooled BEC | 1 | I.Riu | Will be rented at CERN pool | 500 | 500 | 0 | 400
1.2 | P3 backplane | 2 | L.Fayard | Produced at LAL | 1500 | 3000 | 3000 | 0
1.3 | VME 9U for INJ and TTC | 1 | G.Perrot | Will be rented at CERN pool | 500 | 500 | 0 | 600
1.4 | VME 9U water cooled BEC | 1 | I.Riu | Ordered | 12000 | 12000 | 12000 | 0
1.5 | Water filter | 1 | B.Laforge | To be ordered | 120 | 120 | 0 | 120
1.6 | Water distribution unit | 1 | B.Laforge | To be produced | 0 | 0 | 0 | 0
1.7 | Water return module | 1 | B.Laforge | To be produced | 0 | 0 | 0 | 0
1.8 | Water tubes etc. | 9 | B.Laforge | To be produced | 0 | 0 | 0 | 0
2. | Computers
2.1 | PC for readout | 1 | L.Poggioli | To be ordered by LAPP | 3000 | 3000 | 3000 | 0
2.2 | PC for monitoring | 1 | L.Poggioli | To be ordered by LAPP | 2000 | 2000 | 2000 | 0
2.3 | VP110 | 2 | L.Kurchaninov | Ordered 29.04.03 | 5620 | 11240 | 11240 | 0
2.4 | FILAR | 3 | L.Poggioli | Will be rented at CERN pool | 150 | 450 | 0 | 450
3. | Injectors, TTC
3.1 | Injector module | 1 | G.Perrot | In design at LAPP | 7800 | 7800 | 0 | 7800
|  | 3 | G.Perrot | In design at LAPP | 7800 | 23400 | 15600 | 7800
3.2 | Optical splitters | 20 | G.Perrot | Ordered by LAPP | 280 | 5600 | 5600 | 0
3.3 | TTCvi module | 2 | B.Laforge | Will be rented at CERN pool | 150 | 300 | 0 | 300
3.4 | TTCex module | 1 | B.Laforge | Will be rented at CERN pool | 150 | 150 | 0 | 150
3.5 | ROD busy module | 1 | B.Laforge | Will be rented at CERN pool | 150 | 150 | 0 | 150
4 | Front-End
4.1 | FE crate | 1 | L.Kurchaninov | Expected from BNL | 0 | 0 | 0 | 0
4.2 | FEB cooling | 1 | B.Laforge | Standard fan trays | 0 | 0 | 0 | 0
4.3 | LV power units | 6 | L.Kurchaninov | Will be borrowed from HEC | 0 | 0 | 0 | 0
4.4 | SPAC bus | 1 | B.Laforge | Existing prototype | 0 | 0 | 0 | 0
4.5 | TTC electrical cable | 1 | B.Laforge | Existing prototype | 0 | 0 | 0 | 0
4.6 | Controller board | 1 | B.Laforge | Existing prototype | 0 | 0 | 0 | 0
4.7 | FEB | 1 | S.Simion | Under tests at Nevis | 0 | 0 | 0 | 0
5. | ROD modules
5.1 | ROD board | 1 | D.LaMarra | Under tests in Ge Uni | 8000 | 8000 | 8000 | 0
|  | 4 | D.LaMarra | To be produced by GE Uni | 8000 | 32000 | 24000 | 8000
5.2 | PU | 4 | L.Poggioli | Under tests at LAPP | 1650 | 6600 | 6600 | 0
|  | 8 | L.Poggioli | To be produced by LAPP | 1650 | 13200 | 6600 | 6600
5.3 | Transition module | 1 | L.Fayard | In production at LAL | 3000 | 3000 | 3000 | 0
|  | 4 | L.Fayard | In production at LAL | 3000 | 12000 | 9000 | 3000
5.4 | TBM | 2 | L.Fayard | In design at LAL | 3000 | 6000 | 6000 | 0
5.5 | SPAC master | 1 | B.Laforge | In design | 0 | 0 | 0 | 0
6. | Optical cables
6.1 | INJ-ROD single 2m | 60 | G.Perrot | To be ordered at CERN Store | 26 | 1560 | 0 | 1560
6.2 | TTC-TBM single 5m | 1 | G.Perrot | To be ordered at CERN Store | 26 | 26 | 0 | 26
6.3 | TTC-INJ single 5m | 4 | G.Perrot | To be ordered at CERN Store | 26 | 104 | 0 | 104
6.4 | TM-FILAR dual 5m | 12 | G.Perrot | To be ordered at CERN Store | 107 | 1284 | 0 | 1284
6.5 | SPAC-Slave single 5m | 4 | G.Perrot | To be ordered at CERN Store | 26 | 104 | 0 | 104
6.6 | FEB-ROD single 5m | 1 | G.Perrot | To be ordered at CERN Store | 26 | 26 | 0 | 26
6.7 | TTC-Contr single 5m | 1 | G.Perrot | To be ordered at CERN Store | 26 | 26 | 0 | 26
7. | Tools
7.1 | DC load (VME module) | 9 | I.Riu | To be borrowed | 0 | 0 | 0 | 0
7.2 | Electrical load of power | 1 | M.Citterio | Exists at INFN | 0 | 0 | 0 | 0
7.3 | P3 termination cards | 15 | L.Fayard | In production | 100 | 1500 | 0 | 1500
7.4 | Optical attenuator | 1 | G.Perrot | To be supplied by SMU | 0 | 0 | 0 | 0
7.5 | Optical power meter | 1 | L.Kurchaninov | To be ordered by MPI | 800 | 800 | 800 | 0
7.6 | RF power meter | 1 |  | Under investigation |  | 0 | 0 | 0
7.6 | Multimeter | 1 | L.Kurchaninov | Common EML equippment | 0 | 0 | 0 | 0
7.7 | Oscilloscope | 1 | L.Kurchaninov | Common EML equippment | 0 | 0 | 0 | 0
7.8 | VME display module | 1 | L.Kurchaninov | Common EML equippment | 0 | 0 | 0 | 0
[7 empty] | Total to share | 40000